CPM Knowledge Quiz — Form A

Post-Session Assessment

TEB3053 IT Project Management| UTP Malaysia

Instructions: Answer all 13 questions. The network reference table is provided below. Show all working for calculation questions. Questions marked are required. This quiz is worth 13 points.

NETWORK REFERENCE TABLE

Use this table for all questions.

| Node | Task | Dur | Pred | ES | EF | LS | LF | TF | FF | Path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirements Analysis | 3 | None | 0 | 3 | 0 | 3 | 0 | 0 | CP |
| B | UI/UX Design | 3 | A | 3 | 6 | 4 | 7 | 1 | 0 | NC |
| C | Database Schema Design | 2 | A | 3 | 5 | 3 | 5 | 0 | 0 | CP |
| D | Backend API Development | 6 | C | 5 | 11 | 5 | 11 | 0 | 0 | CP |
| E | Frontend Development | 4 | B | 6 | 10 | 7 | 11 | 1 | 1 | NC |
| F | API Integration | 3 | D+E | 11 | 14 | 11 | 14 | 0 | 0 | CP |
| G | Unit Testing | 2 | F | 14 | 16 | 14 | 16 | 0 | 0 | CP |
| H | User Acceptance Testing | 3 | G | 16 | 19 | 16 | 19 | 0 | 0 | CP |
| I | Deployment | 1 | H | 19 | 20 | 19 | 20 | 0 | 0 | CP |

Note. Dur = Duration (days). Pred = Predecessors. ES/EF = Early Start/Finish. LS/LF = Late Start/Finish. TF = Total Float. FF = Free Float. CP = Critical Path. NC = Non-Critical. Critical path: A→C→D→F→G→H→I = 20 days.

Q0.  Participant ID

________________________

Section 1 — Float Calculation (Questions 1–3)

Q1.  Calculate the Total Float for Task B. Show your working.

LS − ES  =  ________        Total Float  =  ________

Q2.  Calculate the Total Float for Task E. Show your working.

LS − ES  =  ________        Total Float  =  ________

Q3.  A delay of 2 days occurs on Task D. By how many days will the project end date be extended? Explain your answer.

Explanation:  ___________________________________________________________

Section 2 — Critical Path Identification (Questions 4–6)

Select one answer for each question.

Q4.  Which of the following is the correct critical path for this project?

A.  A → B → E → F → G → H → I

B.  A → C → D → F → G → H → I

C.  A → C → D → E → F → G → H → I

D.  A → B → D → F → G → H → I

Q5.  What is the total duration of the critical path?

A.  19 days

B.  20 days

C.  21 days

D.  18 days

Q6.  Which tasks have non-zero Total Float?

A.  Tasks A and C

B.  Tasks B and E

C.  Tasks D and F

D.  Tasks G and H

Section 3 — Dependency Sequencing (Questions 7–9)

Q7.  Task F cannot begin until which two tasks are both complete?

A.  Tasks C and E

B.  Tasks D and E

C.  Tasks B and D

D.  Tasks A and C

Q8.  Which task has the earliest start date of Day 11?

A.  Task E

B.  Task G

C.  Task F

D.  Task D

Q9.  If Task C is delayed by 1 day, which tasks are directly affected?

A.  Tasks B and E

B.  Tasks D, F, G, H, and I

C.  Task F only

D.  No tasks are affected

Section 4 — Schedule Impact Analysis (Questions 10–12)

Q10.  Task B has a Total Float of 1 day. What does this mean in practical terms?

Answer:  ________________________________________________________________

Q11.  Task E has an Early Start of Day 6 and a Late Start of Day 7. What is the significance of this difference?

Answer:  ________________________________________________________________

Q12.  Which single task should be shortened to compress the schedule by 1 day, and why?

Task:  ___________    Reason:  ___________________________________________

Section 5 — Conceptual Understanding (Question 13)

Q13.  Define Total Float in your own words and explain why a project manager should pay close attention to tasks with zero Total Float. Write at least two sentences.

Answer:  ________________________________________________________________