CPM Knowledge Quiz — Form B

Post-Session Assessment

TEB3053 IT Project Management | UTP Malaysia

Instructions: Answer all 13 questions. The network reference table is provided below. Show all working for calculation questions. Questions marked are required. This quiz is worth 13 points.

NETWORK REFERENCE TABLE

Use this table for all questions.

| Node | Task | Dur | Pred | ES | EF | LS | LF | TF | FF | Path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirements Analysis | 3 | None | 0 | 3 | 0 | 3 | 0 | 0 | CP |
| B | UI/UX Design | 3 | A | 3 | 6 | 4 | 7 | 1 | 0 | NC |
| C | Database Schema Design | 2 | A | 3 | 5 | 3 | 5 | 0 | 0 | CP |
| D | Backend API Development | 6 | C | 5 | 11 | 5 | 11 | 0 | 0 | CP |
| E | Frontend Development | 4 | B | 6 | 10 | 7 | 11 | 1 | 1 | NC |
| F | API Integration | 3 | D+E | 11 | 14 | 11 | 14 | 0 | 0 | CP |
| G | Unit Testing | 2 | F | 14 | 16 | 14 | 16 | 0 | 0 | CP |
| H | User Acceptance Testing | 3 | G | 16 | 19 | 16 | 19 | 0 | 0 | CP |
| I | Deployment | 1 | H | 19 | 20 | 19 | 20 | 0 | 0 | CP |

Note. Dur = Duration (days). Pred = Predecessors. ES/EF = Early Start/Finish. LS/LF = Late Start/Finish. TF = Total Float. FF = Free Float. CP = Critical Path. NC = Non-Critical. Critical path: A→C→D→F→G→H→I = 20 days.

Q0.  Participant ID

________________________

Section 1 — Float Calculation (Questions 1–3)

Q1.  Calculate the Free Float for Task E. Show your working.

ES of successor (Task F) − EF of Task E  =  ________        Free Float  =  ________

Q2.  Task D has a duration of 6 days and starts on Day 5. On what day does it finish? What is its Total Float?

Early Finish  =  ________        Total Float  =  ________

Q3.  If Task B is delayed by 2 days, what happens to the project end date? Explain using float values.

Explanation:  ___________________________________________________________

Section 2 — Critical Path Identification (Questions 4–6)

Select one answer for each question.

Q4.  Which path represents the non-critical path in this project?

A.  A → C → D → F → G → H → I

B.  A → B → E → F → G → H → I

C.  A → B → D → F → G → H → I

D.  A → C → E → F → G → H → I

Q5.  Which task is the convergence point where both paths meet?

A.  Task D

B.  Task E

C.  Task F

D.  Task G

Q6.  What is the duration of the non-critical path?

A.  17 days

B.  18 days

C.  19 days

D.  20 days

Section 3 — Dependency Sequencing (Questions 7–9)

Q7.  Which task must be completed before Task C can begin?

A.  Task B

B.  Task A

C.  Task D

D.  Task E

Q8.  Task H has a Late Start of Day 16. What does this mean?

A.  Task H can start as early as Day 16

B.  Task H must start no later than Day 16 without delaying the project

C.  Task H has 16 days of float

D.  Task H finishes on Day 16

Q9.  Which task has the longest duration on the critical path?

A.  Task A

B.  Task H

C.  Task D

D.  Task F

Section 4 — Schedule Impact Analysis (Questions 10–12)

Q10.  Task F is the convergence point of the two paths. What are the implications if Task F is delayed by 1 day?

Answer:  ________________________________________________________________

Q11.  The Early Start of Task F is Day 11. Explain why this is the case given its two predecessors.

Answer:  ________________________________________________________________

Q12.  A team member proposes adding 1 day to Task B to improve UI/UX quality. Will this extend the project end date? Justify your answer.

Answer (Yes / No):  ________    Justification:  __________________________

Section 5 — Conceptual Understanding (Question 13)

Q13.  Explain in your own words what happens at a convergence point and why the project manager must monitor both predecessor tasks of Task F. Write at least two sentences.

Answer:  ________________________________________________________________