CPM Knowledge Quiz — Form C

Retention Assessment

TEB3053 IT Project Management | UTP Malaysia

Instructions: Answer all 13 questions. The network reference table is provided below. Show all working for calculation questions. Questions marked are required. This quiz is worth 13 points.

NETWORK REFERENCE TABLE

Use this table for all questions.

| Node | Task | Dur | Pred | ES | EF | LS | LF | TF | FF | Path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirements Analysis | 3 | None | 0 | 3 | 0 | 3 | 0 | 0 | CP |
| B | UI/UX Design | 3 | A | 3 | 6 | 4 | 7 | 1 | 0 | NC |
| C | Database Schema Design | 2 | A | 3 | 5 | 3 | 5 | 0 | 0 | CP |
| D | Backend API Development | 6 | C | 5 | 11 | 5 | 11 | 0 | 0 | CP |
| E | Frontend Development | 4 | B | 6 | 10 | 7 | 11 | 1 | 1 | NC |
| F | API Integration | 3 | D+E | 11 | 14 | 11 | 14 | 0 | 0 | CP |
| G | Unit Testing | 2 | F | 14 | 16 | 14 | 16 | 0 | 0 | CP |
| H | User Acceptance Testing | 3 | G | 16 | 19 | 16 | 19 | 0 | 0 | CP |
| I | Deployment | 1 | H | 19 | 20 | 19 | 20 | 0 | 0 | CP |

Note. Dur = Duration (days). Pred = Predecessors. ES/EF = Early Start/Finish. LS/LF = Late Start/Finish. TF = Total Float. FF = Free Float. CP = Critical Path. NC = Non-Critical. Critical path: A→C→D→F→G→H→I = 20 days.

Q0.  Participant ID

________________________

Section 1 — Float Calculation (Questions 1–3)

Q1.  What is the Total Float of Task B? What is the Total Float of Task E? Show your working for both.

Task B Total Float  =  ________        Task E Total Float  =  ________

Q2.  Calculate the Late Finish of Task D. Show your working.

Working:  __________________________________________    Late Finish  =  ________

Q3.  If both Task B and Task E are each delayed by 1 day, what is the new project end date? Explain your reasoning.

New project end date:  ________

Reasoning:  _____________________________________________________________

Section 2 — Critical Path Identification (Questions 4–6)

Select one answer for each question.

Q4.  Which task has both zero Total Float and zero Free Float, and is NOT the project start or end?

A.  Task B

B.  Task E

C.  Task D

D.  Task G

Q5.  How many tasks are on the critical path?

A.  5

B.  6

C.  7

D.  8

Q6.  Which statement correctly describes the relationship between the two paths at Task F?

A.  Task F starts when the faster path arrives

B.  Task F starts when both Task D and Task E are complete

C.  Task F starts when Task D is complete regardless of Task E

D.  Task F has float because it depends on two predecessors

Section 3 — Dependency Sequencing (Questions 7–9)

Q7.  What is the earliest that Task G can begin, and why?

A.  Day 11 — because Task F finishes on Day 14

B.  Day 14 — because Task F finishes on Day 14

C.  Day 16 — because Task G has Late Start of Day 14

D.  Day 12 — because Task G has 2 days float

Q8.  Which two tasks can be worked on in parallel during Day 3 to Day 6?

A.  Tasks C and D

B.  Tasks B and C

C.  Tasks D and E

D.  Tasks A and B

Q9.  If Task A is delayed by 1 day, how many tasks are affected and which are they?

Number of tasks affected:  ________    Tasks:  _____________________________

Section 4 — Schedule Impact Analysis (Questions 10–12)

Q10.  Task E has 1 day of Free Float and 1 day of Total Float. Explain what this tells us about Task E's relationship with Task F.

Answer:  ________________________________________________________________

Q11.  A stakeholder requests that Task H be extended by 2 days. What is the impact on the project end date?

Impact:  _______________    Reason:  _____________________________________

Q12.  Rank Task B, Task D, Task F, and Task E from highest to lowest scheduling risk. Justify your ranking.

Ranking (highest risk first) & Justification:  ___________________________________________

Section 5 — Conceptual Understanding (Question 13)

Q13.  Explain the difference between a critical path task and a non-critical task and describe what a project manager should do differently when monitoring each type. Write at least two sentences.

Answer:  ________________________________________________________________